## Task List (hidden)
RESEARCH TASK TRACKER
[9 empty] | Initials: | NB | Breitwieser | BR | Reamer
[10 empty] | NP | Poplavskyy | WM | Maney
DATE ADDED | GROUP | TASK | SUBTASKS | SUSPENSE | WHO | STATUS | NOTES
End of Fall 25 |  | Speed verification, tap into encoder |  |  |  | Rejected (state why in comments) | Didn't work due to slow DAQ -- NB tried
|  | Fix double hitting, make consistent good over range of speeds |  |  |  | In-progress
|  | voltage shifter (3.3V to 5V) |  |  |  | Not started | if there's time
|  | run high frequency tests on pigpio | 40,000 steps/rev |  |  | Not started
|  | benchmark the pi with pigpio |  |  |  | In-progress
|  | Hit something else using pigpio and compare consistency | move station to old herrick |  |  | Not started
2026-01-29 |  | fix wobble in hammer | make aluminum insert |  | NB | Completed (no ARR)
|  | Make UI on MATLAB |  |  |  | Not started | confirm with Gibert if he wants the UI on MATLAB
|  | Performance curves for big hammer | test on panel |  |  | Not started
|  | Extend hammer mount | 3d printer |  | WM | In-progress
|  | SAMH use in Trailer | Discuss with Gibert |  | BR | Not started | How should it be utilized to hit the trailer? Interior/Exterior? Isolated from Trailer to eliminate interference from motor Freq? Recommend table with diff length legs and adjustable
|  | finalize motor mount | Design |  | BR | In-progress
|  | Get Pi to work on a 2nd computer |  |  | NP | Not started
|  | Send code to BR |  |  | NP | Completed (no ARR)
2026-02-03 |  | write calibration code |  |  |  | In-progress
|  | write 2-way comm code | test with mini gui |  |  | Not started
2026-02-06 |  | Send buy order to Karsten | 90deg connector - NB has link |  | NB | Not started
talk to Dr G to drill holes in marble table and if it will go under the same ticket as Karsten's work
2026-02-12 |  | change all units to SPM |  |  | NP
|  | drill holes in marble table |  |  | NB, BR
improve gui
redesign motor mount for 90 deg connector
2026-03-13 |  | auto launch code on bootup, so user doesn't need to open vnc view |  |  | NP
|  | make equipment board |  |  | BR
|  | make project box |  |  | BR
Testing all the hammer tips for big and small hammer (performance curves)
|  | upgrading motor mount |  |  | BR
|  | upgrading hammer mount for 90deg connector |  |  | WM
|  | fix overrotation for high force inputs (>2kN) |  |  | NP
|  | Test double hit code |  |  | NP
ask gibert about why force is need to get 4-5 modal frequency spikes
ask gibert about safety write-up
ask gibert about using different forces at different laser locations for maximum excitation
2026-04-02 |  | make poster | make outline
map it out
divide sections
write that shi
edit that shi
print that di
Outline
Abstract/Overview
[7 empty] | Motivation | manual testing is non-repeatable, and existing systems are very expensive
Background
[7 empty] | Process | design process
Results
[7 empty] | Conclusions | real world applications

## Manual Hit Testing Results (hidden)
Force (N) | DH? | MEAN | SD
117.4 | N | 197.6623 | 31.2314
176.02 | N
166.97 | N
161.08 | N
195.91 | N
151.16 | N
175.48 | N
197 | Y
171.05 | Y
117.9 | N
192.3 | Y
181.1 | Y
213.9 | N
196.1 | N
174.5 | N
201.6 | N
153.6 | N
194.3 | N
207.5 | N
167.1 | N
211.6 | N
180 | N
222.4 | N
231.9 | N
202.1 | N
246 | N
168.5 | N
192.4 | N
222.92 | N
195.14 | Y
222 | N
185.7 | Y
180.8 | Y
227.4 | N
267.2 | N
186.2 | N
255.7 | N
232.6 | N
144.62 | N
201.97 | N
204.83 | N
228.32 | N
219.4 | N
288.5 | N
203.15 | Y
243.9 | Y
217.24 | N
288.03 | N
196.58 | Y
183.49 | N
205.3 | Y
202.4 | N
209.75 | Y
208.3 | N
232.54 | N
193.93 | N
192.48 | N
166.25 | N
195.08 | N
164.42 | N
183.3 | N
197.92 | N
152.95 | N
192.57 | N
173.53 | N
205.46 | Y
195.37 | N
205.84 | N
217.21 | N
216.92 | N
187.14 | N
202.88 | N
180.73 | N
182.18 | N

## Orders (hidden)
Item | Link
Breakout board | https://www.digikey.com/en/products/detail/seeed-technology-co-ltd/114992565/13635853?gclsrc=aw.ds&gad_source=1&gad_campaignid=20243136172&gbraid=0AAAAADrbLlihVj4K8yFeuroc6Bo3VfvP-&gclid=CjwKCAiAv5bMBhAIEiwAqP9GuK3dkkd3yLwZgDn0ni2t0Ah3fUn-6KDSlx6YVf9s3tTlqBLTRBdLAxoCrKIQAvD_BwE
12" M/M jumper wires | https://www.digikey.com/en/products/detail/sparkfun-electronics/09387/5993849
90 Degree BNC connector | https://www.digikey.com/en/products/detail/amphenol-rf/31-9-RFX/100653

## Change Log (hidden)
Date | What issue to solve | Change | Observation | Results
2025-12-04 | Hits being "fat", solve double hitting on slow speeds, increase power for hammer to retract to minimize contact time | Change back accelration to constant over different speeds
2025-12-04 | Change PID control to "B" from "D"
2025-12-04 | Issue with holding speed at end? | Decrease acceleration distance to 50% of travel
2025-12-04 | Issue with double hitting / precision | Change steps/rev to 6400

## F vs RPM Curves
Big Hammer |  |  | Test surface: Semi-truck panel in old HERL
|  |  | Steps/rev: | 1600
Red Tip (Hard)
RPM | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | Average | STD
6 | 152.2 | 151.7 | 151.6 | 152.4 | 153.7 | 152.32 | 0.84083
8 | 201.8 | 208.6 | 210 | 209.3 | 209.1 | 207.76 | 3.3694
10 | 258.5 | 256.3 | 258.3 | 257.6 | 256.9 | 257.52 | 0.92844
12 | 303.7 | 320.1 | 316 | 309.5 | 308.7 | 311.6 | 6.4583
14 | 355.2 | 360.2 | 362.1 | 362.5 | 361.4 | 360.28 | 2.971
16 | 422.2 | 416.9 | 417.1 | 415.4 | 414.8 | 417.28 | 2.9184
18 | 472.5 | 471.9 | 472.8 | 471.5 | 472 | 472.14 | 0.51284
20 | 535.4 | 538 | 538 | 538.1 | 538.1 | 537.52 | 1.1862
Green Tip (Med)
RPM | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | Average | STD | deviation | Baseline Corrected Value
6 | 96.3 | 96.5 | 96.4 | 96.5 | 96.5 | 96.44 | 0.089443 | 11 | 106.94
8 | 153.8 | 151.9 | 152.5 | 152.3 | 152.9 | 152.68 | 0.7225 | 10.5 | 163.18
10 | 176.6 | 173.2 | 173.3 | 173.5 | 173.4 | 174 | 1.4577 | 10.5 | 184.5
12 | 219.4 | 224.1 | 224.3 | 224 | 222.9 | 222.94 | 2.0526 |  | 233.44
14 | 265.9 | 269.1 | 268.2 | 268.6 | 268.7 | 268.1 | 1.2708 |  | 278.6
16 | 315.9 | 314.5 | 311.6 | 312.6 | 310.5 | 313.02 | 2.1811 |  | 323.52
18 | 359.5 | 359 | 358.9 | 358.2 | 359.8 | 359.08 | 0.614 |  | 369.58
20 | 414.8 | 414.5 | 417.8 | 414.4 | 415.8 | 415.46 | 1.4206 |  | 425.96
Orange Tip (Soft)
RPM | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | Average | STD |  | Baseline Corrected Value
6 | 48.5 | 47.9 | 47.2 | 48.1 | 48.1 | 47.96 | 0.47749 | -11 | 58.96
8 | 80.8 | 80.6 | 80.4 | 80.7 | 80.6 | 80.62 | 0.14832 | -10 | 91.62
10 | 96.2 | 94.8 | 94.6 | 94.6 | 94.7 | 94.98 | 0.68702 |  | 105.98
12 | 121.7 | 123.5 | 124.1 | 123.5 | 124 | 123.36 | 0.9685 |  | 134.36
14 | 150.9 | 151.9 | 151.7 | 151.9 | 152.1 | 151.7 | 0.46904 |  | 162.7
16 | 179.2 | 177.7 | 178.5 | 178.7 | 177.3 | 178.28 | 0.76942 |  | 189.28
18 | 207.8 | 207 | 207.1 | 207 | 207.4 | 207.26 | 0.34351 |  | 218.26
20 | 238.9 | 238.8 | 237.6 | 237.9 | 237.8 | 238.2 | 0.60415 |  | 249.2
Test parameters:
| Big factor | 4347.862 | N/V
| Small factor | 444.444 | N/v
Small Hammer
Metal Tip
RPM | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | Average | STD
2 | 18.1 | 18.4 | 18.1 | 18.2 | 18 | 18.16 | 0.15166
4 | 30.9 | 31.7 | 32.6 | 31.8 | 32.6 | 31.92 | 0.71204
6 | 51.4 | 50.8 | 50.3 | 51.3 | 51.7 | 51.1 | 0.55227
8 | 70.1 | 69.4 | 68.5 | 69.7 | 69.6 | 69.46 | 0.59414
10 | 87.8 | 87.5 | 89.4 | 88.5 | 88.7 | 88.38 | 0.75299
Plastic Tip
RPM | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | Average | STD
2 | 11.3 | 11.7 | 11.7 | 11.8 | 11.7 | 11.64 | 0.19494
4 | 26.2 | 25.7 | 25.7 | 25.6 | 26.7 | 25.98 | 0.46583
6 | 35.9 | 36.3 | 36.3 | 36 | 36.4 | 36.18 | 0.21679
8 | 50.9 | 50.9 | 50.7 | 51.3 | 52 | 51.16 | 0.51769
10 | 65.2 | 65.9 | 64.5 | 63.8 | 64.5 | 64.78 | 0.79812
Calibration
Desired force | Cal 1 avg | Cal 2 avg | Cal 3 avg
150N, 5 hits, 2% tolerance | 173 | 144 | 151

## Big Hammer Tests
One Step from Test Subject | [7 empty] | Force (N)
Steps/Rev | Start Speed (rpm) | Speed increment (rpm) | Top Speed (rpm) | Steps/ramp level | Step Cap (to reduce waiting) | Steps of Acceleration | Step Distance | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | AVG | STDDEV | avg V
1600 | 5 | 1 | 8 | 133 | 20 | 60 | 800 | 159.9 | 150.9 | 158.5 | 137.4 | 158.4 | 152.7783 | 8.4236 | 0.035139 | rpm = (x+160.2)/40.056
1600 | 5 | 1 | 10 | 80 | 20 | 100 | 800 | 228.9 | 252.6 | 236.6 | 257.5 | 261 | 247.0031 | 12.4328 | 0.056811
1600 | 5 | 1 | 12 | 57 | 20 | 140 | 800 | 311.1 | 326.3 | 308.8 | 324.5 | 312.2 | 316.4961 | 7.3068 | 0.072794 | 500
1600 | 5 | 1 | 14 | 44 | 20 | 180 | 800 | 396.6 | 394.9 | 389.9 | 403.8 | 391.9 | 395.3911 | 4.7906 | 0.09094
1600 | 5 | 1 | 16 | 36 | 20 | 220 | 800 | 477.3 | 483.3 | 470.7 | 484.7 | 478.6 | 478.8943 | 4.9576 | 0.11015
1600 | 5 | 1 | 18 | 30 | 20 | 260 | 800 | 573 | 574.3 | 574.1 | 567.4 | 569.2 | 571.5932 | 2.7893 | 0.13147
1600 | 5 | 1 | 20 | 26 | 20 | 300 | 800 | 642.62 | 642.99 | 649.06 | 641.09 | 650.19 | 645.1794 | 3.6941 | 0.14839
1600 | 5 | 1 | 22 | 23 | 20 | 340 | 800 | 723.42 | 728.95 | 718.15 | 717.55 | 722.91 | 722.1842 | 4.1371 | 0.1661
1600 | 5 | 1 | 24 | 21 | 20 | 380 | 800 | 796.78 | 802.24 | 798.79 | 796.86 | 805.34 | 799.9951 | 3.3234 | 0.184
1600 | 5 | 1 | 26 | 19 | 19 | 399 | 800 | 884.11 | 896.13 | 891.03 | 899.92 | 901.12 | 894.44 | 6.2585 | 0.20572
1600 | 5 | 1 | 28 | 17 | 17 | 391 | 800 | 942.5 | 952.15 | 954.97 | 962.03 | 956.63 | 953.6342 | 6.4408 | 0.21934
1600 | 5 | 1 | 30 | 16 | 16 | 400 | 800 | 1034 | 1041.8 | 1029.8 | 1021.9 | 1036.7 | 1032.8181 | 6.7149 | 0.23755
Two Steps from Test Subject
Steps/Rev | Start Speed (rpm) | Speed increment (rpm) | Top Speed (rpm) | Steps/ramp level | Step Cap (to reduce waiting) | Steps of Acceleration | Step Distance | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | AVG | STDDEV | avg V
1600 | 5 | 1 | 8 | 133 | 20 | 60 | 800 | 150.51 | 123.06 | 131.2 | 126.28 | 130 | 131.88 | 9.5883 | 0.030332
1600 | 5 | 1 | 10 | 80 | 20 | 100 | 800 | 241.84 | 218.24 | 228.81 | 217.29 | 230.35 | 227.1293 | 9.0031 | 0.05224
1600 | 5 | 1 | 12 | 57 | 20 | 140 | 800 | 300.4 | 281.88 | 288.32 | 279.08 | 307.07 | 291.1528 | 10.7558 | 0.066965
1600 | 5 | 1 | 14 | 44 | 20 | 180 | 800 | 376.54 | 376.69 | 362.61 | 365.3 | 365.87 | 369.3536 | 5.9916 | 0.084951
1600 | 5 | 1 | 16 | 36 | 20 | 220 | 800 | 477.43 | 477.69 | 482.23 | 485.54 | 487.36 | 482.0332 | 4.019 | 0.11087
1600 | 5 | 1 | 18 | 30 | 20 | 260 | 800 | 541.76 | 545.78 | 534.88 | 523.54 | 535.01 | 536.1404 | 7.5647 | 0.12331
1600 | 5 | 1 | 20 | 26 | 20 | 300 | 800 | 648.5 | 632.61 | 631.34 | 628.5 | 634.39 | 635.0299 | 6.9851 | 0.14606
1600 | 5 | 1 | 22 | 23 | 20 | 340 | 800 | 706.24 | 702.2 | 700.62 | 689.33 | 695.1 | 698.6731 | 5.8914 | 0.16069
1600 | 5 | 1 | 24 | 21 | 20 | 380 | 800 | 757.43 | 773.55 | 770.97 | 776.19 | 781.9 | 771.9648 | 8.1402 | 0.17755
1600 | 5 | 1 | 26 | 19 | 19 | 399 | 800 | 867.94 | 884.93 | 884.48 | 892.16 | 896.09 | 885.0671 | 9.6488 | 0.20357
1600 | 5 | 1 | 28 | 17 | 17 | 391 | 800 | 949.67 | 951.45 | 964.61 | 935.04 | 942.84 | 948.6712 | 9.8241 | 0.21819
1600 | 5 | 1 | 30 | 16 | 16 | 400 | 800 | 1034.6 | 1034.3 | 1009.2 | 1027.1 | 1015.6 | 1024.1094 | 10.1738 | 0.23555
Zero Steps from Test Subject
Steps/Rev | Start Speed (rpm) | Speed increment (rpm) | Top Speed (rpm) | Steps/ramp level | Step Cap (to reduce waiting) | Steps of Acceleration | Step Distance | Hit 1 | Hit 2 | Hit 3 | Hit 4 | Hit 5 | AVG | STDDEV | avg V
1600 | 5 | 1 | 8 | 133 | 20 | 60 | 800 | 177.4 | 172.81 | 179.33 | 182.63 | 179.64 | 178.3323 | 3.2415 | 0.041016
1600 | 5 | 1 | 10 | 80 | 20 | 100 | 800 | 280.3 | 279.1 | 278.93 | 276.55 | 277.53 | 278.4789 | 1.3059 | 0.06405
1600 | 5 | 1 | 12 | 57 | 20 | 140 | 800 | 344.09 | 334.35 | 324.53 | 329.53 | 338.37 | 334.105 | 6.7903 | 0.076844
1600 | 5 | 1 | 14 | 44 | 20 | 180 | 800 | 425.95 | 411.75 | 411.41 | 409.88 | 412.82 | 414.321 | 5.87 | 0.095294
1600 | 5 | 1 | 16 | 36 | 20 | 220 | 800 | 510.13 | 498.34 | 500.7 | 500.58 | 502.54 | 502.4417 | 4.0606 | 0.11556
1600 | 5 | 1 | 18 | 30 | 20 | 260 | 800 | 576.45 | 558.11 | 558.43 | 561.08 | 558.98 | 562.567 | 6.9969 | 0.12939
1600 | 5 | 1 | 20 | 26 | 20 | 300 | 800 | 650.86 | 650.37 | 653.04 | 651.6 | 655.89 | 652.349 | 1.9855 | 0.15004
1600 | 5 | 1 | 22 | 23 | 20 | 340 | 800 | 716.32 | 737.49 | 741.15 | 737.79 | 741.39 | 734.7672 | 9.3961 | 0.169
1600 | 5 | 1 | 24 | 21 | 20 | 380 | 800 | 764.97 | 779.74 | 785.92 | 782.61 | 778.94 | 778.4028 | 7.1655 | 0.17903
1600 | 5 | 1 | 26 | 19 | 19 | 399 | 800 | 888.32 | 894.83 | 895.21 | 901.89 | 900.56 | 896.149 | 4.8235 | 0.20611
1600 | 5 | 1 | 28 | 17 | 17 | 391 | 800 | 967.14 | 986.2 | 971.9 | 969.4 | 975.4 | 973.9852 | 6.6847 | 0.22402
1600 | 5 | 1 | 30 | 16 | 16 | 400 | 800 | 1067.6 | 1052.3 | 1039.4 | 1046.4 | 1025.2 | 1046.0861 | 14.0175 | 0.2406
1 step away from Test Subject |  |  | re-zeroed
Input force of 500-> force output |  |  | Input force of 500-> force output
500 | 495.71 |  | 500 | 496.89 |  | 500 | 490.78 |  | 700 | 701.99 |  | 200 | 189.09
500 | 511.92 |  | 500 | 488.7 |  | 500 | 496.99 |  | 700 | 697.83 |  | 200 | 193.3
500 | 510.5 |  | 500 | 491.44 |  | 500 | 487.31 |  | 700 | 707.85 |  | 200 | 192.88
500 | 493.93 |  | 500 | 489.81 |  | 500 | 487.69 |  | 700 | 692.94 |  | 200 | 191.32
500 | 492.56 |  | 500 | 488.9 |  | 500 | 487.51 |  | 700 | 697.31 |  | 200 | 190.36
[9 empty] | 700 | 696.74

## Max Frequency Test @ 6400 (hidden)
| test 1 | test 2 | test 3 | avg
1600 | 11.326 | 9.186 | 11.082 | 10.5313
#DIV/0!
4800 | 52.133 | 49.33 | 47.984 | 49.8157
6400 | 72.666 | 69.301 | 69.945 | 70.6373
8000 | 79.281 | 81.4 | 79.619 | 80.1
9600 | 98.14 | 97.15 | 94.11 | 96.4667
11200 | 98.37 | 105.57 | 105.82 | 103.2533
12800 | 118.07 | 114.67 | 112.57 | 115.1033
14400 | 125.49 | 124.87 | 129.07 | 126.4767
16000 | 127.53 | 127.49 | 111.17 | 122.0633
17600 | 85.34 | 85.67 | 90.27 | 87.0933
19200 | 87.71 | 92.48 | 93.32 | 91.17
20800 | 94.63 | 90.96 | 91.02 | 92.2033
22400 | 106.75 | 93.28 | 102.62 | 100.8833
24000 | 103.08 | 100.72 | 102.24 | 102.0133
25600 | 109.32 | 103.46 | 107.91 | 106.8967
27200 |  | 118.56 | 117 | 117.78
28800 | 121.08 | 116.79 | 121.54 | 119.8033
30400 | 117.79 | 123.79 | 124.25 | 121.9433
32000 | 126 | 124.77 | 129.32 | 126.6967
33600 | 128.86 | 125.25 | 130.23 | 128.1133
35200 | 125.77 | 134.7 | 140.47 | 133.6467
36800 | 128.71 | 129.7 | 129.71 | 129.3733
38400 | 138.03 | 134.91 | 131 | 134.6467

## 3200 stepsrev (hidden)
STEP/SEC | FORCE 1 | FORCE 2 | FORCE 3 | FORCE 4 | FORCE 5 | AVERAGE | STDDEV
400 | [5 empty] | #DIV/0! | #DIV/0!
600 | [5 empty] | #DIV/0! | #DIV/0!
800 | [5 empty] | #DIV/0! | #DIV/0!
1000 | [5 empty] | #DIV/0! | #DIV/0!
1200 | [5 empty] | #DIV/0! | #DIV/0!
1400 | [5 empty] | #DIV/0! | #DIV/0!
1600 | [5 empty] | #DIV/0! | #DIV/0!
1800 | [5 empty] | #DIV/0! | #DIV/0!
2000 | [5 empty] | #DIV/0! | #DIV/0!
2200 | [5 empty] | #DIV/0! | #DIV/0!
2400 | [5 empty] | #DIV/0! | #DIV/0!
2600 | [5 empty] | #DIV/0! | #DIV/0!
2800 | [5 empty] | #DIV/0! | #DIV/0!
3000 | [5 empty] | #DIV/0! | #DIV/0!
3200 | [5 empty] | #DIV/0! | #DIV/0!

## Steps per rev adjustments
Steps/Rev | Speed (rev/s) | Force (N) |  |  |  |  | AVG | STDDEV | avg mV
200 | 1 | 92.1 | 92.791 | 95.394 |  | 92.47 | 93.1887 | 1.497 | 209.8846
200 | 2 | 181.06 | 188.16 | 191.25 | 182.64 | 181.24 | 184.87 | 4.5879 | 416.3739
200 | 3 | 335.56 | 336.94 | 335.39 | 328.57 | 328.5 | 332.992 | 4.1129 | 749.982
200 | 4 | 505.68 | 492.08 | 477.97 | 506.43 | 504.98 | 497.428 | 12.3832 | 1120.3333
200 | 5 | 666.06 | 671.87 | 672.34 | 658.38 | 659.87 | 665.704 | 6.5165 | 1499.3333
200 | 6 | 832.31 | 826.3 | 809.04 | 832.04 | 792.274 | 818.3928 | 17.4078 | 1843.227
200 | 7 | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
200 | 8 | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
200 | 9 | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
200 | 10 | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0!
7.7509
800 | 1 | 91.79 | 107.48 | 76.09 | 92.54 | 90.79 | 91.738 | 11.1155 | 206.6171
800 | 2 | 175.14 | 177.07 | 185.71 | 184.26 | 198.25 | 184.086 | 9.1179 | 414.6081
800 | 3 | 281.82 | 305.34 | 289.03 | 300.87 | 284.35 | 292.282 | 10.3345 | 658.2928
800 | 4 | 392.26 | 409.4 | 401.85 | 404.17 | 405.61 | 402.658 | 6.427 | 906.8874
800 | 5 | 487.37 | 500.27 | 496.5 | 492.75 | 495.72 | 494.522 | 4.8135 | 1113.7883
800 | 6 | 670.43 | 580.59 | 572.17 | 572.21 | 572.11 | 593.502 | 43.1586 | 1336.7162
800 | 7 | 651.15 | 649.52 | 649.92 | 653.64 | 670.87 | 655.02 | 9.0051 | 1475.2703
800 | 8 | 719.03 | 717.58 | 696.56 | 741.99 | 718.29 | 718.69 | 16.079 | 1618.6712
800 | 9 | 806.07 | 789.61 | 816.4 | 793.28 | 792.67 | 799.606 | 11.3123 | 1800.9144
800 | 10 | 871.98 | 854.54 | 868.03 | 883.22 | 859.37 | 867.428 | 11.1971 | 1953.6667
13.256
1600 | 1 | 87.101 | 85.074 | 85.811 | 86.209 | 85.994 | 86.0378 | 0.73177 | 193.7788
1600 | 2 | 161.62 | 156.88 | 163.82 | 162.06 | 164.09 | 161.694 | 2.8972 | 364.1757
1600 | 3 | 248.66 | 244.97 | 245.83 | 231.23 | 235.93 | 241.324 | 7.3892 | 543.5225
1600 | 4 | 324.47 | 318.94 | 299.2 | 290.56 | 290.6 | 304.754 | 15.9892 | 686.3829
1600 | 5 | 365.92 | 344.22 | 342.66 | 348.73 | 348.89 | 350.084 | 9.2674 | 788.4775
1600 | 6 | 391.8 | 385.22 | 391.98 | 399.87 | 382.64 | 390.302 | 6.7294 | 879.0586
1600 | 7 | 438.87 | 441.25 | 433.76 | 438.72 | 432.78 | 437.076 | 3.633 | 984.4054
1600 | 8 | 492.28 | 474.57 | 458.22 | 473.88 | 469.4 | 473.67 | 12.2894 | 1066.8243
1600 | 9 | 528.12 | 495.79 | 512.25 | 501.71 | 502.89 | 508.152 | 12.6246 | 1144.4865
1600 | 10 | 553.84 | 549.07 | 519.84 | 556.27 | 536.79 | 543.162 | 15.0438 | 1223.3378
8.6595
3200 | 1 | 96.307 | 94.021 | 94.155 | 93.69 | 94.91 | 94.6166 | 1.0452 | 213.1005
3200 | 2 | 128.1 | 141.14 | 141.28 | 140.27 | 141.82 | 138.522 | 5.8526 | 311.9865
3200 | 3 | 188.25 | 201.51 | 203.69 | 203.73 | 160.64 | 191.564 | 18.4476 | 431.4505
3200 | 4 | 237.66 | 247.3 | 251.13 | 249.45 | 247.72 | 246.652 | 5.2511 | 555.5225
3200 | 5 | 279.25 | 280.04 | 278.87 | 279.31 | 274.17 | 278.328 | 2.3626 | 626.8649
3200 | 6 | 300.78 | 297.69 | 300.14 | 296.56 | 298.18 | 298.67 | 1.7511 | 672.6802
3200 | 7 | 314.69 | 318.82 | 316.16 | 319.95 | 319.73 | 317.87 | 2.3305 | 715.9234
3200 | 8 | 348.7 | 338.22 | 338.95 | 328.33 | 330.72 | 336.984 | 8.0123 | 758.973
3200 | 9 | 346.6 | 344.33 | 349.66 | 355.46 | 356.31 | 350.472 | 5.2995 | 789.3514
3200 | 10 | 366.84 | 355.04 | 362.35 | 372.9 | 358.24 | 363.074 | 7.0564 | 817.7342
5.7409

## Sheet1 (hidden)
Input Force | Actual Force (N) | test 2: quicker speed off of part |  | test 3: even faster speed off part |  | Test 4:linear speed off the part
1 | 45.79 | Input Force | Actual Force (N) | Input Force | Actual Force (N) | Input Force | Actual Force (N) | Input Force | Actual Force (N)
1 | 46.859 | 1 | 48.292 | 1 | 46.989 | 1 | 47.866 | 1 | 47.825
1 | 46.185 | 1 | 46.506 | 1 | 45.798 | 1 | 48.105 | 1 | 48.046
1 | 49.045 | 1 | 47.406 | 1 | 44.958 | 1 | 47.985 | 1 | 47.881
1 | 48.625 | 1 | 46.338 | 1 | 44.714 | 1 | 47.712 | 1 | 47.712
1 | 48.054 | 1 | 47.111 | 1 | 41.167 | 1 | 47.999 | 1 | 48.434
[8 empty] | 2 | 29.179 | 2 | 43.753
[8 empty] | 2 | 46.972 | 2 | 46.897
[8 empty] | 2 | 42.726 | 2 | 39.163
[8 empty] | 2 | 46.723 | 2 | 40.269
[8 empty] | 2 | 40.952 | 2 | 46.987
[8 empty] | 3 | 36.24
[8 empty] | 3 | 38.704
3
3
3